## Home
Complete Responsive Project Management Environment
Excel PMO system with desktop, compact, governance and project command views
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Start Here
Executive Dashboard | Full desktop PMO dashboard
Compact Dashboard | Smaller-screen quick dashboard
Project Command Center | Single project selector view
Projects | Portfolio master
Tasks | Task tracking
Kanban | Status board
Gantt | Timeline view
Change Requests | Change control
Approvals | Approval tracker
RACI Matrix | Role clarity
Reports | PMO reports

## Portfolio_Dashboard
Portfolio Dashboard
High-standard PMO dashboard for multiple projects
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Total Projects |  |  | Active Projects |  |  | At Risk / Overdue |  |  | Completed Projects
Open Issues |  |  | Open Risks |  |  | Logged Hours |  |  | Budget Variance
Project Health |  |  | Task Status |  |  | Priority Mix |  |  | User Workload
Health | Count |  | Status | Count |  | Priority | Count |  | User | Active Tasks
On Track |  |  | On Track |  |  | Critical
At Risk |  |  | At Risk |  |  | High
Overdue |  |  | Overdue |  |  | Medium
Blocked |  |  | Blocked |  |  | Low
Completed |  |  | Completed
Not Started |  |  | Not Started
Portfolio List
Project ID | Project | Status | Priority | Progress | Health | Open Issues | Open Risks | Hours

## Project_Workspace
Project Workspace
Single-project command center: choose project ID in B5
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Select Project ID | PRJ-001
Project Name |  |  | Manager |  |  | Status |  |  | Health
Progress |  |  | Open Issues |  |  | Open Risks |  |  | Logged Hours
Project Task Snapshot
Task ID | Task Name | Owner | Status | Priority | Progress | Health | Due Date
Recent Activity
Date | Type | User | Task | Comment

## Projects
Projects
Multi-project portfolio master
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Project ID | Project Name | Client ID | Team ID | Project Manager | Start Date | End Date | Manual Status | Priority | Budget | Actual Cost | Task Count | Completed Tasks | Open Issues | Open Risks | Logged Hours | Progress % | Auto Health | Days Remaining | Project Group | Notes
PRJ-001 | ERP Modernization | CL-001 | TEAM-001 | USR-001 | 2026-04-30 | 2026-07-29 | In Progress | Critical | 750000 | 280000 | [8 empty] | Strategic | Core ERP transformation
PRJ-002 | Customer Portal | CL-002 | TEAM-001 | USR-001 | 2026-05-20 | 2026-07-14 | In Progress | High | 320000 | 85000 | [8 empty] | Customer Experience | Self-service portal
PRJ-003 | Data Quality Program | CL-003 | TEAM-002 | USR-004 | 2026-04-05 | 2026-06-29 | Planning | Medium | 150000 | 45000 | [8 empty] | Governance | Data quality remediation
PRJ-004 | Branch Ops Automation | CL-004 | TEAM-003 | USR-005 | 2026-05-30 | 2026-08-18 | Not Started | High | 410000 | 20000 | [8 empty] | Automation | Workflow automation
PRJ-005 | Mobile App Refresh | CL-002 | TEAM-001 | USR-003 | 2026-03-11 | 2026-06-04 | Completed | Medium | 180000 | 175000 | [8 empty] | Experience | Mobile UX refresh
Formulas:
Days Remaining = MAX(0,[@[End Date]]-TODAY())

## Tasks
Tasks
Project-aware task list with dependencies and health
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Task ID | Project ID | Task Name | Category | Assigned User | Start Date | Due Date | Manual Status | Priority | Progress % | Depends On Task ID | Blocked? | Blocking Reason | Sprint / Phase | Subtask Count | Completed Subtasks | Issue Count | Logged Hours | Auto Health | Days Late | Notes
TSK-001 | PRJ-001 | Requirements workshop | Requirement | USR-001 | 2026-05-05 | 2026-05-20 | Completed | High | 100% |  | No |  | Sprint 1
TSK-002 | PRJ-001 | Integration design | Design | USR-003 | 2026-05-22 | 2026-06-14 | In Progress | Critical | 65% | TSK-001 | No |  | Sprint 2
TSK-003 | PRJ-001 | Build Oracle connector | Development | USR-002 | 2026-06-03 | 2026-06-27 | In Progress | Critical | 32% | TSK-002 | No |  | Sprint 2
TSK-004 | PRJ-002 | Portal wireframes | Design | USR-003 | 2026-05-25 | 2026-06-07 | Completed | High | 100% |  | No |  | Sprint 1
TSK-005 | PRJ-002 | Authentication module | Development | USR-002 | 2026-06-01 | 2026-07-01 | Blocked | High | 20% | TSK-004 | Yes | Security review pending | Sprint 2
TSK-006 | PRJ-003 | Data profiling | Research | USR-004 | 2026-04-15 | 2026-06-01 | In Progress | Medium | 70% |  | No |  | Phase 1
TSK-007 | PRJ-003 | Remediation plan | Documentation | USR-006 | 2026-06-04 | 2026-06-19 | Not Started | Medium | 0% | TSK-006 | No |  | Phase 1
TSK-008 | PRJ-004 | Workflow mapping | Requirement | USR-006 | 2026-06-05 | 2026-06-21 | In Progress | High | 35% |  | No |  | Discovery
TSK-009 | PRJ-004 | Pilot deployment | Deployment | USR-005 | 2026-06-19 | 2026-07-24 | Not Started | High | 0% | TSK-008 | No |  | Pilot
TSK-010 | PRJ-005 | Release closure | Deployment | USR-005 | 2026-05-20 | 2026-06-04 | Completed | Medium | 100% |  | No |  | Closure
Formulas:
Days Late = IF(AND([@[Due Date]]<TODAY(),[@[Manual Status]]<>"Completed"),TODAY()-[@[Due Date]],0)

## Subtasks
Subtasks
Detailed execution checklist
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Subtask ID | Parent Task ID | Project ID | Subtask Name | Assigned User | Due Date | Manual Status | Priority | Completion % | Auto Health | Days Late
SUB-001 | TSK-002 | PRJ-001 | Interface inventory | USR-003 | 2026-06-11 | In Progress | High | 70%
SUB-002 | TSK-003 | PRJ-001 | Connection pool | USR-002 | 2026-06-17 | Not Started | Critical | 0%
SUB-003 | TSK-005 | PRJ-002 | SSO spike | USR-002 | 2026-06-15 | Blocked | High | 15%
SUB-004 | TSK-006 | PRJ-003 | Profile customer table | USR-004 | 2026-06-05 | In Progress | Medium | 80%
SUB-005 | TSK-008 | PRJ-004 | Current-state process map | USR-006 | 2026-06-14 | In Progress | High | 45%
Formulas:
Auto Health = IF([@[Manual Status]]="Completed","Completed",IF(AND([@[Due Date]]<TODAY(),[@[Manual Status]]<>"Completed"),"Overdue",IF(AND([@[Due Date]]-TODAY()<=3,[@[Completion %]]<0.8),"At Risk",IF([@[Completion %]]=0,"Not Started","On Track"))))
Days Late = IF(AND([@[Due Date]]<TODAY(),[@[Manual Status]]<>"Completed"),TODAY()-[@[Due Date]],0)

## Milestones
Milestones
Major checkpoints and delivery gates
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Milestone ID | Project ID | Milestone Name | Owner | Target Date | Manual Status | Priority | Auto Health | Days Remaining
MS-001 | PRJ-001 | Architecture sign-off | USR-001 | 2026-06-21 | In Progress | Critical
MS-002 | PRJ-002 | Portal beta | USR-001 | 2026-07-04 | Not Started | High
MS-003 | PRJ-003 | DQ baseline approved | USR-004 | 2026-06-13 | In Progress | Medium
MS-004 | PRJ-004 | Pilot go-live | USR-005 | 2026-07-29 | Not Started | High
MS-005 | PRJ-005 | Closure accepted | USR-001 | 2026-06-06 | Completed | Medium
Formulas:
Reports = IF([@[Manual Status]]="Completed","Completed",IF(AND([@[Target Date]]<TODAY(),[@[Manual Status]]<>"Completed"),"Overdue",IF([@[Target Date]]-TODAY()<=5,"At Risk","On Track")))
Master = MAX(0,[@[Target Date]]-TODAY())

## Issues
Issues
Zoho-style issue and blocker register
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Issue ID | Project ID | Task ID | Type | Title | Owner | Priority | Status | Created Date | Due Date | Age Days | Auto Health | Notes
ISS-001 | PRJ-001 | TSK-003 | Dependency | Oracle access delay | USR-002 | High | In Progress | 2026-06-07 | 2026-06-12 |  |  | Need DBA approval
ISS-002 | PRJ-002 | TSK-005 | Blocker | Security sign-off pending | USR-001 | Critical | Open | 2026-06-04 | 2026-06-10 |  |  | Escalated to security
ISS-003 | PRJ-003 | TSK-006 | Bug | Missing source ownership | USR-004 | Medium | Waiting | 2026-05-30 | 2026-06-15 |  |  | Waiting data steward
ISS-004 | PRJ-004 | TSK-008 | Change Request | Add approval workflow | USR-006 | Medium | Open | 2026-06-08 | 2026-06-23 |  |  | Scope review
Formulas:
Age Days = TODAY()-[@[Created Date]]
Auto Health = IF([@[Status]]="Closed","Completed",IF([@[Status]]="Resolved","Completed",IF(AND([@[Due Date]]<TODAY(),[@[Status]]<>"Closed",[@[Status]]<>"Resolved"),"Overdue",IF([@[Priority]]="Critical","At Risk","On Track"))))

## Risks
Risks
Risk register with mitigation tracking
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Risk ID | Project ID | Risk Title | Owner | Probability | Impact | Severity | Mitigation | Status | Risk Score
RSK-001 | PRJ-001 | Legacy schema unknowns | USR-002 | High | Medium | High | Run profiling spike | Mitigating
RSK-002 | PRJ-002 | Security approval may slip | USR-001 | High | High | Critical | Escalate weekly | Escalated
RSK-003 | PRJ-003 | Low business owner availability | USR-004 | Medium | High | Medium | Set governance cadence | Open
RSK-004 | PRJ-004 | Pilot adoption risk | USR-005 | Medium | Medium | Medium | Training and hypercare | Open

## Timesheets
Timesheets
Project and task time tracking
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Entry ID | Project ID | Task ID | User ID | Work Date | Hours | Billable | Work Description
TIME-001 | PRJ-001 | TSK-002 | USR-003 | 2026-06-08 | 6 | Billable | Design review
TIME-002 | PRJ-001 | TSK-003 | USR-002 | 2026-06-08 | 7 | Billable | Connector build
TIME-003 | PRJ-002 | TSK-005 | USR-002 | 2026-06-07 | 5 | Billable | Auth spike
TIME-004 | PRJ-003 | TSK-006 | USR-004 | 2026-06-06 | 4 | Non-Billable | Data profiling
TIME-005 | PRJ-004 | TSK-008 | USR-006 | 2026-06-09 | 6 | Billable | Workshop notes

## Calendar
Calendar
Upcoming due dates across all projects
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Item Type | Project ID | Item ID | Title | Owner | Due Date | Status | Health
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task

## Kanban_View
Kanban View
Status board-style task view
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Not Started | In Progress | Blocked | In Review | Completed

## Activity_Log
Activity Log
Project activity stream and comments
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Activity ID | Project ID | Task ID | Activity Type | User ID | Activity Date | Comment / Update
ACT-001 | PRJ-001 | TSK-003 | Comment | USR-002 | 2026-06-08 | Connector design shared for review
ACT-002 | PRJ-002 | TSK-005 | Escalation | USR-001 | 2026-06-08 | Security review escalated
ACT-003 | PRJ-003 | TSK-006 | Status Change | USR-004 | 2026-06-07 | Profiling moved to in progress
ACT-004 | PRJ-004 | TSK-008 | Meeting | USR-006 | 2026-06-09 | Workflow discovery meeting completed

## Documents
Documents
Document and file reference register
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Document ID | Project ID | Document Type | Document Name | Owner | Upload Date | Link / Location
DOC-001 | PRJ-001 | BRD | ERP requirements | USR-001 | 2026-05-10 | SharePoint/ERP-BRD
DOC-002 | PRJ-002 | Design | Portal wireframes | USR-003 | 2026-06-02 | Figma/Portal
DOC-003 | PRJ-003 | Report | DQ baseline | USR-004 | 2026-06-06 | Drive/DQ
DOC-004 | PRJ-004 | Minutes | Workshop notes | USR-006 | 2026-06-09 | Drive/Ops

## Users
Users
Resource directory and calculated workload
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
User ID | Full Name | Email | Department | Role | Availability | Capacity Hours/Week | Assigned Tasks | Active Tasks | Overdue Tasks | Logged Hours | Utilization %
USR-001 | Aarav Sharma | aarav@example.com | PMO | Project Manager | Available | 40
USR-002 | Meera Iyer | meera@example.com | Engineering | Developer | Busy | 40
USR-003 | Rohan Gupta | rohan@example.com | Design | Designer | Available | 35
USR-004 | Nisha Rao | nisha@example.com | QA | QA Engineer | Available | 40
USR-005 | Vikram Menon | vikram@example.com | Operations | DevOps | Busy | 40
USR-006 | Fatima Khan | fatima@example.com | Support | Business Analyst | Available | 40

## Teams
Teams
Zoho-style teams/squads
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Team ID | Team Name | Lead User | Department | Notes
TEAM-001 | Platform Squad | USR-001 | Engineering | Core app delivery
TEAM-002 | Quality Guild | USR-004 | QA | Testing and release assurance
TEAM-003 | Operations Cell | USR-005 | Operations | Deployment and support

## Clients
Clients
Client and department master
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Client ID | Client / Department | Type | Contact Name | Contact Email
CL-001 | Finance Department | Internal | Anjali Verma | anjali@example.com
CL-002 | Sales Department | Internal | Raj Mehta | raj@example.com
CL-003 | Operations Group | Internal | Kiran Rao | kiran@example.com
CL-004 | External Client A | External | Divya Shah | divya@example.com

## Reports
Reports
Ready-to-use PMO reports
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Overdue Tasks
Task ID | Project ID | Task | Owner | Due Date | Days Late | Priority
User Workload
User | Department | Active Tasks | Overdue Tasks | Logged Hours | Utilization

## Master_Management
Master Management
Central dropdown lists for every module
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Project_Status | Task_Status | Priority | Health | Issue_Status | Issue_Type | Risk_Status | Billable | Department | Role | Activity_Type | Document_Type
Not Started | Not Started | Critical | On Track | Open | Bug | Open | Billable | PMO | Project Manager | Comment | BRD
Planning | In Progress | High | At Risk | In Progress | Change Request | Mitigating | Non-Billable | Engineering | Business Analyst | Status Change | Design
In Progress | Blocked | Medium | Overdue | Waiting | Support | Accepted |  | Design | Developer | File Uploaded | Test Evidence
On Hold | On Hold | Low | Blocked | Resolved | Dependency | Closed |  | QA | Designer | Meeting | SOP
Completed | In Review |  | Completed | Closed | Decision | Escalated |  | Operations | QA Engineer | Approval | Minutes
Cancelled | Completed |  | Not Started | Rejected | Blocker |  |  | Finance | DevOps | Escalation | Contract
Archived | Cancelled | [6 empty] | Sales | Stakeholder | Decision | Report
[8 empty] | Support | Approver |  | Other
[8 empty] | HR | Finance Owner
Legal

## Settings
Settings
Workbook configuration and report controls
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
Company Name | Your Company
Default Currency | INR
Reporting Date
Portfolio Owner | PMO
Default Working Week | Mon-Fri
Version | 2.0 Zoho-style workspace

## How_To_Use
How To Use
Operating notes for the Zoho-style workbook
Home | Dashboard | Workspace | Projects | Tasks | Issues | Timesheets | Reports | Master
1 | Start from Home or Portfolio Dashboard for overall navigation.
2 | Use Projects as the portfolio master; every task, issue, risk, milestone, document and timesheet row links back to Project ID.
3 | Use Project Workspace to pick one Project ID and view its task snapshot and activity stream.
4 | Use Kanban View for a simple status board.
5 | Use Timesheets for effort tracking and Reports for overdue/workload outputs.
6 | Add dropdown values in Master Management before expanding company-specific fields.

## Executive_Dashboard
Executive Dashboard
Desktop PMO dashboard for portfolio leadership
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Total Projects |  |  | Active Projects |  |  | At Risk / Overdue |  |  | Completed Projects
Open Issues |  |  | Open Risks |  |  | Logged Hours |  |  | Budget Variance
Project Health |  |  | Task Status |  |  | Priority Mix |  |  | User Workload
Health | Count |  | Status | Count |  | Priority | Count |  | User | Active Tasks
On Track |  |  | On Track |  |  | Critical
At Risk |  |  | At Risk |  |  | High
Overdue |  |  | Overdue |  |  | Medium
Blocked |  |  | Blocked |  |  | Low
Completed |  |  | Completed
Not Started |  |  | Not Started
Portfolio List
Project ID | Project | Status | Priority | Progress | Health | Open Issues | Open Risks | Hours

## Project_Command_Center
Project Command Center
Single-project command center with project selector
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Select Project ID | PRJ-001
Project Name |  |  | Manager |  |  | Status |  |  | Health
Progress |  |  | Open Issues |  |  | Open Risks |  |  | Logged Hours
Project Task Snapshot
Task ID | Task Name | Owner | Status | Priority | Progress | Health | Due Date
Recent Activity
Date | Type | User | Task | Comment

## Compact_Dashboard
Compact Dashboard
Responsive-style quick view for smaller screens
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Projects |  | Active |  | Overdue |  | Issues
Risks |  | Hours |  | Blocked |  | Budget Var
Next Actions
Type | Project | Item | Owner | Due | Health
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task
Task

## Project_Charter
Project Charter
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Charter ID | Project ID | Business Objective | Scope Summary | Success Criteria | Sponsor | Approval Status | Approved Date
CHR-001 | PRJ-001 | Modernize ERP operations | Replace legacy integration and automate reporting | Stable go-live with <2% defects | USR-001 | Approved | 2026-05-05
CHR-002 | PRJ-006 | Regulatory reporting automation | Automate compliance pack generation | On-time monthly regulatory reports | USR-006 | Draft

## Deliverables
Deliverables
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Deliverable ID | Project ID | Deliverable | Owner | Due Date | Status | Acceptance Criteria | Approval Status
DEL-001 | PRJ-001 | Integration design pack | USR-003 | 2026-06-17 | In Progress | Signed architecture document | Submitted
DEL-002 | PRJ-002 | Portal beta build | USR-002 | 2026-07-04 | Not Started | Beta available to pilot users | Draft
DEL-003 | PRJ-006 | Compliance report template | USR-006 | 2026-06-29 | Not Started | Approved by compliance officer | Draft

## Change_Requests
Change Requests
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Change ID | Project ID | Title | Requester | Request Date | Status | Priority | Estimated Cost | Reason
CR-001 | PRJ-002 | Add biometric login | USR-001 | 2026-06-05 | Under Review | High | 65000 | Security requirement
CR-002 | PRJ-004 | Add regional approval route | USR-006 | 2026-06-07 | Draft | Medium | 25000 | Ops request

## Approvals
Approvals
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Approval ID | Project ID | Approval Item | Requester | Approver | Submitted Date | Status | Notes
APR-001 | PRJ-001 | Architecture sign-off | USR-001 | USR-007 | 2026-06-08 | Submitted | Pending finance review
APR-002 | PRJ-002 | Security design | USR-001 | USR-005 | 2026-06-06 | Rework Required | Need auth details
APR-003 | PRJ-005 | Closure approval | USR-001 | USR-007 | 2026-06-02 | Approved | Closed

## RACI_Matrix
RACI Matrix
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
RACI ID | Project ID | Workstream | Activity | Responsible | Accountable | Consulted | Informed
RACI-001 | PRJ-001 | Integration | Oracle connector | USR-002 | USR-001 | USR-005 | USR-007
RACI-002 | PRJ-002 | Security | Authentication | USR-002 | USR-001 | USR-005 | USR-006
RACI-003 | PRJ-006 | Compliance | Report matrix | USR-006 | USR-001 | USR-007 | USR-004

## Stakeholders
Stakeholders
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Stakeholder ID | Project ID | Name | Role | Influence | Cadence | Owner
STK-001 | PRJ-001 | Finance Sponsor | Sponsor | High | Weekly | USR-001
STK-002 | PRJ-002 | Sales Head | Sponsor | High | Weekly | USR-001
STK-003 | PRJ-006 | Compliance Officer | Approver | Critical | Twice Weekly | USR-006

## Communication_Plan
Communication Plan
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Comm ID | Project ID | Communication | Channel | Frequency | Owner | Audience
COM-001 | PRJ-001 | Steering update | Meeting | Weekly | USR-001 | Sponsor group
COM-002 | PRJ-002 | Build status | Email | Twice Weekly | USR-002 | Project team
COM-003 | PRJ-006 | Regulatory review | Meeting | Weekly | USR-006 | Compliance team

## Meeting_Actions
Meeting Actions
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Action ID | Project ID | Action Item | Owner | Due Date | Status | Notes
ACT-001 | PRJ-001 | Confirm Oracle grants | USR-002 | 2026-06-11 | Open | DBA dependency
ACT-002 | PRJ-002 | Resolve security comments | USR-001 | 2026-06-10 | Open | Auth review
ACT-003 | PRJ-003 | Assign data owners | USR-004 | 2026-06-14 | Open | Governance

## Decision_Log
Decision Log
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Decision ID | Project ID | Decision | Owner | Decision Date | Status | Category
DEC-001 | PRJ-001 | Use CDB/PDB Oracle architecture | USR-001 | 2026-05-30 | Approved | Architecture
DEC-002 | PRJ-002 | Use SSO provider | USR-001 | 2026-06-07 | Pending | Security
DEC-003 | PRJ-006 | Monthly compliance pack format | USR-006 | 2026-06-09 | Draft | Reporting

## Lessons_Learned
Lessons Learned
PMO governance module
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Lesson ID | Project ID | Lesson | Owner | Date | Category
LL-001 | PRJ-005 | Design approval earlier reduces rework | USR-003 | 2026-06-04 | Process
LL-002 | PRJ-001 | DBA access must be requested before sprint start | USR-002 | 2026-06-08 | Dependency

## Data_Dictionary
Data Dictionary
Purpose of each worksheet
Home | Exec | Compact | Project | Tasks | Kanban | Gantt | Reports | Master
Sheet | Purpose
Home | Project management environment module
Portfolio_Dashboard | Project management environment module
Project_Workspace | Project management environment module
Projects | Project management environment module
Tasks | Project management environment module
Subtasks | Project management environment module
Milestones | Project management environment module
Issues | Project management environment module
Risks | Project management environment module
Timesheets | Project management environment module
Calendar | Project management environment module
Kanban_View | Project management environment module
Activity_Log | Project management environment module
Documents | Project management environment module
Users | Project management environment module
Teams | Project management environment module
Clients | Project management environment module
Reports | Project management environment module
Master_Management | Project management environment module
Settings | Project management environment module
How_To_Use | Project management environment module
Executive_Dashboard | Project management environment module
Project_Command_Center | Project management environment module
Compact_Dashboard | Project management environment module
Project_Charter | Project management environment module
Deliverables | Project management environment module
Change_Requests | Project management environment module
Approvals | Project management environment module
RACI_Matrix | Project management environment module
Stakeholders | Project management environment module
Communication_Plan | Project management environment module
Meeting_Actions | Project management environment module
Decision_Log | Project management environment module
Lessons_Learned | Project management environment module
Data_Dictionary | Project management environment module