## Project Dashboard
Software Delivery Project Management Dashboard
Project ID | All |  | Project Status | All | Priority | All |  | Risk Level | All
Total Projects |  | Active Projects |  | Completed | Delayed |  | Overall Completion |  | High Risk
Status | Count
Not Started
Active
On Hold
Completed
Delayed
Cancelled

## Gantt Chart
Task ID | Project ID | Module | Task Description | Assigned To | Start Date | Due Date | Status | Completion % | Delay Days

## Project Master
Project ID | Project Name | Client / Bank Name | Project Manager | Start Date | Planned End Date | Revised End Date | Actual End Date | Project Status | Priority | Completion % | Current Phase | Risk Level | Remarks
PRJ-001 | Mobile Banking Revamp | Apex Bank | Ananya Rao | 2026-01-06 | 2026-06-28 | 2026-07-12 |  | Active | High |  | UAT | High | UAT defects under triage
PRJ-002 | Loan Origination Workflow | Crescent Finance | Rohit Menon | 2026-02-03 | 2026-08-15 |  |  | Active | Critical |  | Development | Critical | Integration dependency with CBS
PRJ-003 | Regulatory Reporting Portal | Northstar Bank | Meera Iyer | 2025-11-10 | 2026-04-30 | 2026-05-08 | 2026-05-06 | Completed | High |  | Closed | Medium | Delivered
PRJ-004 | Customer Onboarding App | Horizon Credit Union | Vikram Shah | 2026-03-17 | 2026-07-31 | 2026-08-21 |  | Delayed | High |  | Testing | High | API performance issue open

## Task Tracker
Task ID | Project ID | Module Name | Task Description | Assigned To | Start Date | Due Date | Actual Completion Date | Status | Priority | Dependency | Completion % | Delay Days | Remarks
TSK-001 | PRJ-001 | Login | Implement biometric login | Priya Nair | 2026-01-20 | 2026-03-10 | 2026-03-08 | Completed | High |  | 100% |  | Released
TSK-002 | PRJ-001 | Payments | UPI limit enhancement | Arjun Patel | 2026-03-15 | 2026-05-30 |  | In Progress | High | TSK-001 | 78% |  | Awaiting review
TSK-003 | PRJ-002 | Workflow | Credit approval rules engine | Leena Das | 2026-02-15 | 2026-06-05 |  | Delayed | Critical |  | 64% |  | Slow migration
TSK-004 | PRJ-004 | Onboarding | KYC OCR validation | Imran Ali | 2026-04-01 | 2026-05-25 |  | Delayed | High |  | 70% |  | Accuracy issue
Formulas:
Delay Days = IF([Due Date]="","",MAX(0,IF([Actual Completion Date]<>"",[Actual Completion Date]-[Due Date],IF([Status]="Completed",0,TODAY()-[Due Date]))))

## Milestone Tracker
Milestone ID | Project ID | Milestone Name | Planned Date | Actual Date | Status | Delay Days | Owner | Remarks
MS-001 | PRJ-001 | UAT Signoff | 2026-06-18 |  | At Risk |  | Ananya Rao | Open defects remain
MS-002 | PRJ-002 | SIT Entry | 2026-06-25 |  | Delayed |  | Rohit Menon | Integration blocked
Formulas:
Delay Days = IF([Planned Date]="","",MAX(0,IF([Actual Date]<>"",[Actual Date]-[Planned Date],IF([Status]="Completed",0,TODAY()-[Planned Date]))))

## Issue Tracker
Issue ID | Project ID | Issue Description | Raised By | Raised Date | Assigned To | Severity | Status | Target Resolution Date | Actual Resolution Date | Delay Days | Remarks
ISS-001 | PRJ-001 | Payment confirmation timeout | QA Team | 2026-05-29 | Arjun Patel | High | In Progress | 2026-06-12 |  |  | Fix in review
ISS-002 | PRJ-002 | CBS sandbox unavailable | Integration Lead | 2026-05-20 | Nikhil Verma | Critical | Open | 2026-06-05 |  |  | Escalated
Formulas:
Delay Days = IF([Target Resolution Date]="","",MAX(0,IF([Actual Resolution Date]<>"",[Actual Resolution Date]-[Target Resolution Date],IF(OR([Status]="Resolved",[Status]="Closed"),0,TODAY()-[Target Resolution Date]))))

## Risk Register
Risk ID | Project ID | Risk Description | Impact | Probability | Risk Score | Risk Level | Mitigation Plan | Owner | Status | Remarks
RSK-001 | PRJ-001 | UAT defect leakage may delay release | 4 | 4 |  |  | Daily defect review | Ananya Rao | Open
RSK-002 | PRJ-002 | Vendor API readiness risk | 5 | 5 |  |  | Executive escalation | Rohit Menon | Open

## Resource Tracker
Resource Name | Role | Project ID | Module | Allocation % | Start Date | End Date | Current Workload | Remarks
Priya Nair | Frontend Engineer | PRJ-001 | Login | 60% | 2026-01-20 | 2026-07-12
Arjun Patel | Backend Engineer | PRJ-001 | Payments | 80% | 2026-03-15 | 2026-07-12
Leena Das | Business Analyst | PRJ-002 | Workflow | 75% | 2026-02-15 | 2026-08-15

## Change Request Tracker
CR ID | Project ID | Change Description | Requested By | Requested Date | Impact Analysis | Effort Estimate | Approval Status | Target Date | Status | Remarks
CR-001 | PRJ-001 | Add transaction nickname field | Business | 2026-05-10 | Medium UI/API impact | 6 days | Approved | 2026-06-20 | In Progress

## UAT Testing Tracker
Test Case ID | Project ID | Module | Test Scenario | Tester | Test Date | Result | Defect ID | Retest Status | Remarks
TC-001 | PRJ-001 | Payments | Verify successful UPI payment | QA Analyst 1 | 2026-06-02 | Fail | ISS-001 | Pending | Timeout observed

## Deployment Tracker
Deployment ID | Project ID | Environment | Deployment Date | Version | Deployed By | Deployment Status | Rollback Required | Remarks
DEP-001 | PRJ-003 | Production | 2026-05-06 | v1.0.0 | Release Manager | Completed | No | Successful release

## Lists
Project Status | Task Status | Milestone Status | Issue Status | Priority | Risk Level | Severity | Approval Status | Test Result | Retest Status | Deployment Status | Yes No | Phase | Environment | ImpactProbability | People | Project IDs
Not Started | Not Started | Not Started | Open | Low | Low | Low | Pending | Not Run | Pending | Planned | Yes | Initiation | Development | 1 | Priya Nair | PRJ-001
Active | In Progress | In Progress | In Progress | Medium | Medium | Medium | Approved | Pass | Pass | Successful | No | Requirements | SIT | 2 | Arjun Patel | PRJ-002
On Hold | Blocked | Completed | Resolved | High | High | High | Rejected | Fail | Fail | Failed |  | Design | UAT | 3 | Leena Das | PRJ-003
Completed | Completed | Delayed | Closed | Critical | Critical | Critical | Deferred | Blocked | Not Required | Rolled Back |  | Development | Pre-Production | 4 | Nikhil Verma | PRJ-004
Delayed | Delayed | At Risk | Reopened | [6 empty] | Completed |  | Testing | Production | 5 | Imran Ali
Cancelled | Deferred | [10 empty] | UAT | DR |  | Riya Sen
[12 empty] | Deployment |  |  | Sara Thomas
[12 empty] | Hypercare |  |  | Ananya Rao
[12 empty] | Closed |  |  | Rohit Menon
Meera Iyer
Vikram Shah
Google Sheets note: after importing, use Data > Create a filter if filter arrows are not shown automatically. Dropdowns use inline list validation for better import compatibility.