## Project Dashboard
Software Delivery Portfolio Dashboard
Project ID | All |  | Status | All | Priority | All |  | Risk | All | PM | All
Total Projects |  | Active |  | Completed | Delayed |  | Overall Completion |  | High Risk | Open Issues
Pending Tasks |  | Blocked Tasks |  | Critical Risks | CR Pending |  | Failed Tests |  | Avg Workload | Next 30D Milestones
Status | Count |  | Risk | Count | Priority | Open Tasks |  | Severity | Open Issues
Not Started |  |  | Low |  | Low |  |  | Low
Active |  |  | Medium |  | Medium |  |  | Medium
On Hold |  |  | High |  | High |  |  | High
Completed |  |  | Critical |  | Critical |  |  | Critical
Delayed
Cancelled

## Gantt Chart
Gantt Chart
High-Level Filters | Project ID | All | Status | All | Assigned To | All | Priority | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Task ID | Project ID | Module | Task Description | Assigned To | Start Date | Due Date | Status | Completion % | Delay Days

## Project Master
Project Master
High-Level Filters | Project ID | All | Status | All | Priority | All | Risk | All | PM | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Project ID | Project Name | Client / Bank Name | Project Manager | Start Date | Planned End Date | Revised End Date | Actual End Date | Project Status | Priority | Completion % | Current Phase | Risk Level | Remarks
PRJ-001 | Mobile Banking Revamp | Apex Bank | Ananya Rao | 2026-01-06 | 2026-06-28 | 2026-07-12 |  | Active | High |  | UAT | High | UAT defects under triage
PRJ-002 | Loan Origination Workflow | Crescent Finance | Rohit Menon | 2026-02-03 | 2026-08-15 |  |  | Active | Critical |  | Development | Critical | CBS integration dependency
PRJ-003 | Regulatory Reporting Portal | Northstar Bank | Meera Iyer | 2025-11-10 | 2026-04-30 | 2026-05-08 | 2026-05-06 | Completed | High |  | Closed | Medium | Delivered
PRJ-004 | Customer Onboarding App | Horizon Credit Union | Vikram Shah | 2026-03-17 | 2026-07-31 | 2026-08-21 |  | Delayed | High |  | Testing | High | Performance issue open
PRJ-005 | Treasury Dashboard | Meridian Bank | Fatima Khan | 2026-04-01 | 2026-09-20 |  |  | Active | Medium |  | Design | Medium | Design signoff pending
PRJ-006 | Branch Service Desk Upgrade | Union Trust | Karan Desai | 2025-12-01 | 2026-03-15 |  | 2026-03-14 | Completed | Medium |  | Closed | Low | Completed
PRJ-007 | Fraud Monitoring Rules | Apex Bank | Ananya Rao | 2026-05-10 | 2026-10-15 |  |  | Not Started | Critical |  | Initiation | High | Vendor selection
PRJ-008 | Corporate NetBanking Refresh | Crescent Finance | Rohit Menon | 2026-02-20 | 2026-09-30 | 2026-10-10 |  | On Hold | Medium |  | Requirements | Medium | Budget approval pending

## Task Tracker
Task Tracker
High-Level Filters | Project ID | All | Status | All | Priority | All | Assigned To | All | Module | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Task ID | Project ID | Module Name | Task Description | Assigned To | Start Date | Due Date | Actual Completion Date | Status | Priority | Dependency | Completion % | Delay Days | Remarks
TSK-001 | PRJ-001 | Login | Implement biometric login | Priya Nair | 2026-01-20 | 2026-03-10 | 2026-03-08 | Completed | High |  | 100% |  | Released
TSK-002 | PRJ-001 | Payments | UPI limit enhancement | Arjun Patel | 2026-03-15 | 2026-05-30 |  | In Progress | High | TSK-001 | 78% |  | Security review
TSK-003 | PRJ-002 | Workflow | Credit approval rules engine | Leena Das | 2026-02-15 | 2026-06-05 |  | Delayed | Critical |  | 64% |  | Rule migration
TSK-004 | PRJ-002 | Integration | CBS API integration | Nikhil Verma | 2026-03-01 | 2026-06-20 |  | Blocked | Critical | TSK-003 | 45% |  | Vendor endpoint pending
TSK-005 | PRJ-003 | Reports | RBI compliance report pack | Sara Thomas | 2025-12-01 | 2026-04-10 | 2026-04-08 | Completed | High |  | 100% |  | Validated
TSK-006 | PRJ-004 | Onboarding | KYC OCR validation | Imran Ali | 2026-04-01 | 2026-05-25 |  | Delayed | High |  | 70% |  | Accuracy issue
TSK-007 | PRJ-005 | Dashboard | Treasury exposure view | Riya Sen | 2026-04-15 | 2026-07-15 |  | In Progress | Medium |  | 55% |  | Design changes
TSK-008 | PRJ-006 | Workflow | Branch ticket workflow | Priya Nair | 2025-12-12 | 2026-02-20 | 2026-02-18 | Completed | Medium |  | 100% |  | Closed
TSK-009 | PRJ-007 | Security | Fraud rules baseline | Leena Das | 2026-06-12 | 2026-07-30 |  | Not Started | Critical |  | 0%
TSK-010 | PRJ-008 | Payments | Corporate payment limits | Arjun Patel | 2026-03-10 | 2026-06-30 |  | On Hold | Medium |  | 25% |  | Budget hold
Formulas:
Delay Days = IF([All]="","",MAX(0,IF([Assigned To]<>"",[Assigned To]-[All],IF([All]="Completed",0,TODAY()-[All]))))

## Milestone Tracker
Milestone Tracker
High-Level Filters | Project ID | All | Status | All | Owner | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Milestone ID | Project ID | Milestone Name | Planned Date | Actual Date | Status | Delay Days | Owner | Remarks
MS-001 | PRJ-001 | UAT Signoff | 2026-06-18 |  | At Risk |  | Ananya Rao | Open defects
MS-002 | PRJ-002 | SIT Entry | 2026-06-25 |  | Delayed |  | Rohit Menon | Integration blocked
MS-003 | PRJ-003 | Production Release | 2026-05-05 | 2026-05-06 | Completed |  | Meera Iyer | Released
MS-004 | PRJ-005 | Design Signoff | 2026-06-14 |  | In Progress |  | Fatima Khan | CAB pending
Formulas:
All = IF([Status]="","",MAX(0,IF([All]<>"",[All]-[Status],IF([Owner]="Completed",0,TODAY()-[Status]))))

## Issue Tracker
Issue Tracker
High-Level Filters | Project ID | All | Severity | All | Status | All | Assigned To | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Issue ID | Project ID | Issue Description | Raised By | Raised Date | Assigned To | Severity | Status | Target Resolution Date | Actual Resolution Date | Delay Days | Remarks
ISS-001 | PRJ-001 | Payment confirmation timeout | QA Team | 2026-05-29 | Arjun Patel | High | In Progress | 2026-06-12 |  |  | Fix in review
ISS-002 | PRJ-002 | CBS sandbox unavailable | Integration Lead | 2026-05-20 | Nikhil Verma | Critical | Open | 2026-06-05 |  |  | Escalated
ISS-003 | PRJ-004 | OCR false rejection rate high | QA Team | 2026-05-30 | Imran Ali | High | In Progress | 2026-06-10 |  |  | Tuning
Formulas:
Delay Days = IF([All]="","",MAX(0,IF([Actual Resolution Date]<>"",[Actual Resolution Date]-[All],IF(OR([Assigned To]="Resolved",[Assigned To]="Closed"),0,TODAY()-[All]))))

## Risk Register
Risk Register
High-Level Filters | Project ID | All | Risk Level | All | Owner | All | Status | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Risk ID | Project ID | Risk Description | Impact | Probability | Risk Score | Risk Level | Mitigation Plan | Owner | Status | Remarks
RSK-001 | PRJ-001 | UAT defect leakage may delay release | 4 | 4 |  |  | Daily defect review | Ananya Rao | Open
RSK-002 | PRJ-002 | Vendor API readiness risk | 5 | 5 |  |  | Executive escalation | Rohit Menon | Open
RSK-003 | PRJ-004 | Performance may not meet SLA | 4 | 4 |  |  | Load testing | Vikram Shah | Open
RSK-004 | PRJ-007 | Rules false positives | 4 | 3 |  |  | Model validation | Ananya Rao | Monitoring

## Resource Tracker
Resource Tracker
High-Level Filters | Project ID | All | Resource | All | Module | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Resource Name | Role | Project ID | Module | Allocation % | Start Date | End Date | Current Workload | Remarks
Priya Nair | Frontend Engineer | PRJ-001 | Login | 60% | 2026-01-20 | 2026-07-12
Arjun Patel | Backend Engineer | PRJ-001 | Payments | 80% | 2026-03-15 | 2026-07-12
Leena Das | Business Analyst | PRJ-002 | Workflow | 75% | 2026-02-15 | 2026-08-15
Nikhil Verma | Integration Engineer | PRJ-002 | Integration | 90% | 2026-03-01 | 2026-08-15

## Change Request Tracker
Change Request Tracker
High-Level Filters | Project ID | All | Approval | All | Status | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
CR ID | Project ID | Change Description | Requested By | Requested Date | Impact Analysis | Effort Estimate | Approval Status | Target Date | Status | Remarks
CR-001 | PRJ-001 | Add transaction nickname field | Business | 2026-05-10 | Medium UI/API impact | 6 days | Approved | 2026-06-20 | In Progress
CR-002 | PRJ-005 | Add FX exposure drilldown | Treasury | 2026-05-28 | High reporting impact | 12 days | Pending | 2026-07-10 | Open

## UAT Testing Tracker
UAT Testing Tracker
High-Level Filters | Project ID | All | Module | All | Result | All | Tester | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Test Case ID | Project ID | Module | Test Scenario | Tester | Test Date | Result | Defect ID | Retest Status | Remarks
TC-001 | PRJ-001 | Payments | Verify successful UPI payment | QA Analyst 1 | 2026-06-02 | Fail | ISS-001 | Pending | Timeout
TC-002 | PRJ-003 | Reports | Generate monthly compliance report | QA Analyst 2 | 2026-04-18 | Pass |  | Not Required

## Deployment Tracker
Deployment Tracker
High-Level Filters | Project ID | All | Environment | All | Status | All
Use the dropdown cells above for high-level filtering in Google Sheets with the included Apps Script. Row 4 also has normal column filters.
Deployment ID | Project ID | Environment | Deployment Date | Version | Deployed By | Deployment Status | Rollback Required | Remarks
DEP-001 | PRJ-003 | Production | 2026-05-06 | v1.0.0 | Release Manager | Completed | No | Successful
DEP-002 | PRJ-001 | UAT | 2026-06-01 | v0.9.2 | Release Manager | Successful | No | UAT build

## Lists
Project IDs | People | Modules | Project Status | Task Status | Milestone Status | Issue Status | Priority | Risk Level | Severity | Approval Status | Test Result | Retest Status | Deployment Status | Yes No | Phase | Environment | ImpactProbability
PRJ-001 | Ananya Rao | Login | Not Started | Not Started | Not Started | Open | Low | Low | Low | Pending | Not Run | Pending | Planned | Yes | Initiation | Development | 1
PRJ-002 | Rohit Menon | Payments | Active | In Progress | In Progress | In Progress | Medium | Medium | Medium | Approved | Pass | Pass | Successful | No | Requirements | SIT | 2
PRJ-003 | Meera Iyer | Workflow | On Hold | Blocked | Completed | Resolved | High | High | High | Rejected | Fail | Fail | Failed |  | Design | UAT | 3
PRJ-004 | Vikram Shah | Integration | Completed | Completed | Delayed | Closed | Critical | Critical | Critical | Deferred | Blocked | Not Required | Rolled Back |  | Development | Pre-Production | 4
PRJ-005 | Fatima Khan | Reports | Delayed | Delayed | At Risk | Reopened | [6 empty] | Completed |  | Testing | Production | 5
PRJ-006 | Karan Desai | Onboarding | Cancelled | Deferred | [10 empty] | UAT | DR
PRJ-007 | Priya Nair | Dashboard | [12 empty] | Deployment
PRJ-008 | Arjun Patel | KYC | [12 empty] | Hypercare
| Leena Das | Security | [12 empty] | Closed
| Nikhil Verma | Deployment
Imran Ali
Riya Sen
Sara Thomas
QA Analyst 1
QA Analyst 2
Release Manager
DevOps
Google Sheets: run the companion Apps Script to make the row-2 high-level filters actively filter each sheet.