## Dashboard
Project Management Dashboard
Live summary powered by Projects, Tasks, Subtasks, Milestones, Risks, and Budget sheets
Total Projects |  |  | Active Projects |  | Completed Projects |  |  | Overdue Projects
Total Tasks |  |  | Overdue Tasks |  | Open Risks / Issues |  |  | Budget Variance
Task Status | Count |  | Project Health | Count | Priority | Count |  | User | Active Tasks
Not Started |  |  | On Track |  | Critical
In Progress |  |  | At Risk |  | High
Blocked |  |  | Overdue |  | Medium
On Hold |  |  | Completed |  | Low
Completed |  |  | Not Started
Cancelled |  |  | Blocked
Upcoming Deadlines |  |  |  |  | Overdue Work
Task ID | Project | Task | Owner | Due Date | Task ID | Project | Task | Owner | Days Late

## Master_Management
Master Management
Central dropdown values used throughout the workbook
Project_Status | Task_Status | Priority | Department | Role | Availability | Task_Category | Health | Risk_Type | Severity | Probability | Currency
Not Started | Not Started | Critical | PMO | Project Manager | Available | Requirement | On Track | Risk | Critical | Very High | INR
Planning | In Progress | High | Engineering | Business Analyst | Busy | Design | At Risk | Issue | High | High | USD
In Progress | Blocked | Medium | Design | Developer | On Leave | Development | Overdue | Decision | Medium | Medium | EUR
On Hold | On Hold | Low | QA | Designer | Inactive | Testing | Completed | Dependency | Low | Low | GBP
Completed | Completed |  | Operations | QA Engineer |  | Deployment | Not Started | Assumption |  | Very Low | AED
Cancelled | Cancelled |  | Finance | DevOps |  | Documentation | Blocked |  |  |  | SGD
|  |  | Sales | Stakeholder |  | Meeting
|  |  | Support | Approver |  | Review
|  |  | HR | Finance Owner |  | Support
|  |  | Legal |  |  | Research

## Settings
Settings
Workbook-level configuration
Company Name | Your Company
Reporting Date
Default Currency | INR
Default Working Days | Mon-Fri
Dashboard Version | 1.0
Prepared By | PMO

## Users
Users
Team members, capacity, and calculated workload
User ID | Full Name | Email | Department | Role | Availability | Capacity Hours/Week | Assigned Tasks | Active Tasks | Overdue Tasks | Utilization % | Notes
USR-001 | Aarav Sharma | aarav@example.com | PMO | Project Manager | Available | 40 |  |  |  |  | Program lead
USR-002 | Meera Iyer | meera@example.com | Engineering | Developer | Busy | 40 |  |  |  |  | Backend
USR-003 | Rohan Gupta | rohan@example.com | Design | Designer | Available | 35 |  |  |  |  | UX/UI
USR-004 | Nisha Rao | nisha@example.com | QA | QA Engineer | Available | 40 |  |  |  |  | Testing
USR-005 | Vikram Menon | vikram@example.com | Operations | DevOps | Busy | 40 |  |  |  |  | Release
Note on H3: Formula-driven column. Keep formula when adding new rows.
Note on I3: Formula-driven column. Keep formula when adding new rows.
Note on J3: Formula-driven column. Keep formula when adding new rows.
Note on K3: Formula-driven column. Keep formula when adding new rows.

## Projects
Projects
Portfolio-level project control and calculated health
Project ID | Project Name | Project Manager | Client / Department | Start Date | End Date | Manual Status | Priority | Budget | Actual Cost | Task Count | Completed Tasks | Progress % | Auto Health | Days Remaining | Notes
PRJ-001 | ERP Modernization | USR-001 | Finance | 2026-05-20 | 2026-07-24 | In Progress | Critical | 500000 | 180000 | [5 empty] | Core transformation
PRJ-002 | Customer Portal | USR-001 | Sales | 2026-05-30 | 2026-07-09 | In Progress | High | 220000 | 65000 | [5 empty] | Self-service portal
PRJ-003 | Data Quality Program | USR-001 | Operations | 2026-04-10 | 2026-06-19 | Planning | Medium | 90000 | 25000 | [5 empty] | Data governance
Formulas:
Days Remaining = MAX(0,[@[End Date]]-TODAY())
Note on M3: Formula-driven column. Keep formula when adding new rows.
Note on N3: Formula-driven column. Keep formula when adding new rows.

## Tasks
Tasks
Task management with dependencies, status dropdowns, progress, and auto health
Task ID | Project ID | Task Name | Category | Assigned User | Start Date | Due Date | Manual Status | Priority | Progress % | Depends On Task ID | Blocked? | Blocking Reason | Subtask Count | Completed Subtasks | Auto Health | Days Late | Notes
TSK-001 | PRJ-001 | Requirements workshop | Requirement | USR-001 | 2026-05-22 | 2026-06-04 | Completed | High | 100% | [7 empty] | Done
TSK-002 | PRJ-001 | Integration design | Design | USR-003 | 2026-06-01 | 2026-06-14 | In Progress | Critical | 55% | TSK-001 | No | [5 empty] | API mapping
TSK-003 | PRJ-001 | Build Oracle connector | Development | USR-002 | 2026-06-06 | 2026-06-27 | In Progress | Critical | 25% | TSK-002 | No | [5 empty] | Database connector
TSK-004 | PRJ-002 | Portal wireframes | Design | USR-003 | 2026-05-31 | 2026-06-11 | In Progress | High | 75% |  | No | [5 empty] | UI design
TSK-005 | PRJ-002 | Authentication module | Development | USR-002 | 2026-06-05 | 2026-06-29 | Not Started | High | 0% | TSK-004 | Yes | Waiting for security review |  |  |  |  | SSO
TSK-006 | PRJ-003 | Data profiling | Research | USR-004 | 2026-04-20 | 2026-06-02 | In Progress | Medium | 60% |  | No | [5 empty] | Quality baseline
TSK-007 | PRJ-003 | Remediation plan | Documentation | USR-001 | 2026-06-04 | 2026-06-16 | Not Started | Medium | 0% | TSK-006 | No | [5 empty] | Action plan
Formulas:
Days Late = IF(AND([@[Due Date]]<TODAY(),[@[Manual Status]]<>"Completed"),TODAY()-[@[Due Date]],0)
Note on P3: Formula-driven column. Keep formula when adding new rows.
Note on Q3: Formula-driven column. Keep formula when adding new rows.

## Subtasks
Subtasks
Detailed execution breakdown under tasks
Subtask ID | Parent Task ID | Project ID | Subtask Name | Assigned User | Due Date | Manual Status | Priority | Completion % | Auto Health | Days Late | Notes
SUB-001 | TSK-002 | PRJ-001 | Confirm interfaces | USR-003 | 2026-06-12 | In Progress | Critical | 50% |  |  | Interface list
SUB-002 | TSK-003 | PRJ-001 | Create connection pool | USR-002 | 2026-06-19 | Not Started | High | 0% |  |  | Code task
SUB-003 | TSK-004 | PRJ-002 | Mobile wireframes | USR-003 | 2026-06-10 | Completed | High | 100% |  |  | Approved
SUB-004 | TSK-005 | PRJ-002 | SSO spike | USR-002 | 2026-06-15 | Blocked | High | 10% |  |  | Security dependency
SUB-005 | TSK-006 | PRJ-003 | Profile customer table | USR-004 | 2026-06-05 | In Progress | Medium | 70% |  |  | Late sample
Formulas:
Days Late = IF(AND([@[Due Date]]<TODAY(),[@[Manual Status]]<>"Completed"),TODAY()-[@[Due Date]],0)
Note on J3: Formula-driven column. Keep formula when adding new rows.
Note on K3: Formula-driven column. Keep formula when adding new rows.

## Milestones
Milestones
Major delivery checkpoints
Milestone ID | Project ID | Milestone Name | Owner | Target Date | Actual Date | Manual Status | Priority | Auto Health | Notes
MS-001 | PRJ-001 | Architecture sign-off | USR-001 | 2026-06-21 |  | In Progress | Critical |  | Architecture board
MS-002 | PRJ-002 | Portal beta | USR-001 | 2026-07-04 |  | Not Started | High |  | Beta release
MS-003 | PRJ-003 | DQ baseline approved | USR-004 | 2026-06-13 |  | In Progress | Medium |  | Data owners
Formulas:
Auto Health = IF([@[Manual Status]]="Completed","Completed",IF(AND([@[Target Date]]<TODAY(),[@[Manual Status]]<>"Completed"),"Overdue",IF([@[Target Date]]-TODAY()<=5,"At Risk","On Track")))

## Risks_Issues
Risks & Issues
Risk, issue, dependency, decision, and assumption register
Item ID | Project ID | Type | Title | Owner | Severity | Probability | Impact | Mitigation / Action | Due Date | Manual Status | Auto Health | Notes
RI-001 | PRJ-001 | Risk | Legacy schema unknowns | USR-002 | High | Medium | Migration complexity | Run profiling and spike | 2026-06-23 | Open
RI-002 | PRJ-002 | Dependency | Security review | USR-001 | High | High | Blocks auth module | Schedule security workshop | 2026-06-12 | Open
RI-003 | PRJ-003 | Issue | Missing source ownership | USR-004 | Medium | High | Slow remediation | Assign data stewards | 2026-06-07 | Open
Formulas:
Auto Health = IF([@[Manual Status]]="Closed","Completed",IF(AND([@[Due Date]]<TODAY(),[@[Manual Status]]<>"Closed"),"Overdue",IF([@[Severity]]="Critical","At Risk","On Track")))

## Budget_Effort
Budget & Effort
Planned versus actual cost and hours
Budget ID | Project ID | Cost Category | Planned Hours | Actual Hours | Hours Variance | Planned Cost | Actual Cost | Cost Variance | Variance % | Owner | Notes
BUD-001 | PRJ-001 | Development | 1200 | 430 |  | 500000 | 180000 |  |  | USR-001 | Main build
BUD-002 | PRJ-002 | Development | 650 | 190 |  | 220000 | 65000 |  |  | USR-001 | Portal
BUD-003 | PRJ-003 | Analysis | 300 | 95 |  | 90000 | 25000 |  |  | USR-004 | DQ

## Reports
Reports
Formula-driven report sections
Project Summary
Project ID | Project Name | Manual Status | Auto Health | Progress % | Budget | Actual Cost
User ID | Name | Department | Availability | Active Tasks | Overdue Tasks | Utilization %
Item ID | Project ID | Type | Title | Owner | Severity | Status | Auto Health

## Timeline_Gantt
Timeline / Gantt
Lightweight visual schedule from task start and due dates
Task ID | Project ID | Task Name | Owner | Start Date | Due Date | Status | Progress % | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19

## How_To_Use
How To Use
Operating notes
1 | Add dropdown values in Master_Management first if your company needs custom lists.
2 | Add or update users in Users. Use User ID values when assigning projects/tasks.
3 | Create projects in Projects, then add tasks and subtasks using Project ID and Task ID dropdowns.
4 | Use Manual Status for human tracking. Auto Health calculates schedule risk without overwriting manual status.
5 | Dashboard, Reports, and Timeline update from the source tables. In Excel, formulas recalculate automatically.
6 | Expand any table by typing in the first blank row below it; formulas and dropdowns can be copied down as needed.