## Project Dashboard
Software Delivery Project Management Dashboard
Use the high-level filters below. All dashboard counts, summaries, and charts respond to these selections. | [9 empty] | Last refreshed
Project ID | All | Project Manager | All | Project Status | All | Priority | All | Risk Level | All | Phase | All
Total Projects |  | Active Projects |  | Completed Projects |  | Delayed Projects |  | Overall Completion |  | High-Risk Projects
Upcoming Milestones |  | Pending Tasks |  | Open Issues |  | Critical Risks |  | Avg Workload |  | Overallocated
Project Status Summary |  |  | Risk Summary |  |  | Resource Workload Summary |  |  | Task Priority Summary
Status | Count |  | Risk Level | Count |  | Resource | Workload |  | Priority | Open Tasks
Active |  |  | Low | [5 empty] | Critical
Completed |  |  | Medium | [5 empty] | High
Delayed |  |  | High | [5 empty] | Medium
On Hold |  |  | Critical | [5 empty] | Low
Not Started
Daily Tracking Notes
Filters at the top are intended for high-level management review. Tracker sheets still retain their own table filters for detailed daily tracking.
Formulas:
Project ID = SUMPRODUCT((MilestoneTracker[Milestone ID]<>"")*IF(B3="All",1,--(MilestoneTracker[Project ID]=B3))*--(MilestoneTracker[Planned Date]>=TODAY())*--(MilestoneTracker[Planned Date]<=TODAY()+30)*--(MilestoneTracker[Status]<>"Completed"))

## Gantt Chart
Task Gantt Chart
Project ID | All |  | Task Status | All |  | Assigned To | All
Use the selectors above to filter the task timeline. The weekly Gantt grid and bar chart read from Task Tracker.
Task ID | Project ID | Module | Task Description | Assigned To | Start Date | Due Date | Status | Completion % | Delay Days | Task | Start Offset | Duration

## Lists
ProjectIDs | ProjectIDsAll | ProjectManagers | ProjectManagersAll | Clients | ProjectStatus | ProjectStatusAll | TaskStatus | TaskStatusAll | MilestoneStatus | IssueStatus | Priority | PriorityAll | RiskLevel | RiskLevelAll | Severity | ApprovalStatus | TestResult | RetestStatus | DeploymentStatus | YesNo | Phase | PhaseAll | Resources | ResourcesAll | Owners | Testers | Deployers | Modules | Roles | Environment | ImpactProbability
PRJ-001 | All | Ananya Rao | All | Apex Bank | Not Started | All | Not Started | All | Not Started | Open | Low | All | Low | All | Low | Pending | Not Run | Pending | Planned | Yes | Initiation | All | Priya Nair | All | Ananya Rao | QA Analyst 1 | Release Manager | Login | Frontend Engineer | Development | 1
PRJ-002 | PRJ-001 | Rohit Menon | Ananya Rao | Crescent Finance | Active | Not Started | In Progress | Not Started | In Progress | In Progress | Medium | Low | Medium | Low | Medium | Approved | Pass | Pass | Successful | No | Requirements | Initiation | Arjun Patel | Priya Nair | Rohit Menon | QA Analyst 2 | DevOps | Payments | Backend Engineer | SIT | 2
PRJ-003 | PRJ-002 | Meera Iyer | Rohit Menon | Northstar Bank | On Hold | Active | Blocked | In Progress | Completed | Resolved | High | Medium | High | Medium | High | Rejected | Fail | Fail | Failed |  | Design | Requirements | Leena Das | Arjun Patel | Meera Iyer | Priya Nair |  | Workflow | Business Analyst | UAT | 3
PRJ-004 | PRJ-003 | Vikram Shah | Meera Iyer | Horizon Credit Union | Completed | On Hold | Completed | Blocked | Delayed | Closed | Critical | High | Critical | High | Critical | Deferred | Blocked | Not Required | Rolled Back |  | Development | Design | Imran Ali | Leena Das | Vikram Shah | Arjun Patel |  | Onboarding | Integration Engineer | Pre-Production | 4
| PRJ-004 |  | Vikram Shah |  | Delayed | Completed | Delayed | Completed | At Risk | Reopened |  | Critical |  | Critical |  |  |  |  | Completed |  | Testing | Development | Nikhil Verma | Imran Ali | Priya Nair | Leena Das |  | Integration | ML Engineer | Production | 5
[5 empty] | Cancelled | Delayed | Deferred | Delayed | [12 empty] | UAT | Testing |  | Nikhil Verma | Arjun Patel | Imran Ali |  | KYC |  | DR
[6 empty] | Cancelled |  | Deferred | [12 empty] | Deployment | UAT |  |  | Leena Das | Nikhil Verma |  | Reports
[21 empty] | Hypercare | Deployment |  |  | Imran Ali
[21 empty] | Closed | Hypercare |  |  | Nikhil Verma
Closed
Dropdown source lists. Add new values under the matching column to extend dropdown options.

## Project Master
Project Master
Quick Filters: | Project ID |  | Client / Bank Name |  | Project Manager |  | Project Status |  | Priority
Project ID | Project Name | Client / Bank Name | Project Manager | Start Date | Planned End Date | Revised End Date | Actual End Date | Project Status | Priority | Completion % | Current Phase | Risk Level | Remarks
PRJ-001 | Mobile Banking Revamp | Apex Bank | Ananya Rao | 2026-01-06 | 2026-06-28 | 2026-07-12 |  | Active | High |  | UAT | High | UAT defects under triage
PRJ-002 | Loan Origination Workflow | Crescent Finance | Rohit Menon | 2026-02-03 | 2026-08-15 |  |  | Active | Critical |  | Development | Critical | Integration dependency with CBS
PRJ-003 | Regulatory Reporting Portal | Northstar Bank | Meera Iyer | 2025-11-10 | 2026-04-30 | 2026-05-08 | 2026-05-06 | Completed | High |  | Closed | Medium | Delivered
PRJ-004 | Customer Onboarding App | Horizon Credit Union | Vikram Shah | 2026-03-17 | 2026-07-31 | 2026-08-21 |  | Delayed | High |  | Testing | High | API performance issue open
Note on K3: Completion % averages task completion for the same Project ID.

## Task Tracker
Task Tracker
Quick Filters: | Project ID |  | Module Name |  | Assigned To |  | Status |  | Priority
Task ID | Project ID | Module Name | Task Description | Assigned To | Start Date | Due Date | Actual Completion Date | Status | Priority | Dependency | Completion % | Delay Days | Remarks
TSK-001 | PRJ-001 | Login | Implement biometric login | Priya Nair | 2026-01-20 | 2026-03-10 | 2026-03-08 | Completed | High |  | 100% |  | Released to UAT
TSK-002 | PRJ-001 | Payments | UPI limit enhancement | Arjun Patel | 2026-03-15 | 2026-05-30 |  | In Progress | High | TSK-001 | 78% |  | Awaiting security review
TSK-003 | PRJ-002 | Workflow | Credit approval rules engine | Leena Das | 2026-02-15 | 2026-06-05 |  | Delayed | Critical |  | 64% |  | Rule migration slower than planned
TSK-004 | PRJ-004 | Onboarding | KYC OCR validation | Imran Ali | 2026-04-01 | 2026-05-25 |  | Delayed | High |  | 70% |  | Accuracy issue
Formulas:
Delay Days = IF([Due Date]="","",MAX(0,IF([Status]<>"",[Status]-[Due Date],IF([Status]="Completed",0,TODAY()-[Due Date]))))
Note on M3: Delay Days compares due date with actual completion date or today.

## Milestone Tracker
Milestone Tracker
Quick Filters: | Project ID |  | Status |  | Owner
Milestone ID | Project ID | Milestone Name | Planned Date | Actual Date | Status | Delay Days | Owner | Remarks
MS-001 | PRJ-001 | UAT Signoff | 2026-06-18 |  | At Risk |  | Ananya Rao | Open defects remain
MS-002 | PRJ-002 | SIT Entry | 2026-06-25 |  | Delayed |  | Rohit Menon | Integration blocked
MS-003 | PRJ-003 | Production Release | 2026-05-05 | 2026-05-06 | Completed |  | Meera Iyer | Released
Formulas:
Delay Days = IF([Status]="","",MAX(0,IF([Actual Date]<>"",[Actual Date]-[Status],IF([Owner]="Completed",0,TODAY()-[Status]))))
Note on G3: Delay Days compares planned date with actual date or today.

## Issue Tracker
Issue Tracker
Quick Filters: | Project ID |  | Raised By |  | Assigned To |  | Severity |  | Status
Issue ID | Project ID | Issue Description | Raised By | Raised Date | Assigned To | Severity | Status | Target Resolution Date | Actual Resolution Date | Delay Days | Remarks
ISS-001 | PRJ-001 | Payment confirmation timeout | QA Team | 2026-05-29 | Arjun Patel | High | In Progress | 2026-06-12 |  |  | Fix in review
ISS-002 | PRJ-002 | CBS sandbox unavailable | Integration Lead | 2026-05-20 | Nikhil Verma | Critical | Open | 2026-06-05 |  |  | Escalated
Formulas:
Delay Days = IF([Target Resolution Date]="","",MAX(0,IF([Status]<>"",[Status]-[Target Resolution Date],IF(OR([Severity]="Resolved",[Severity]="Closed"),0,TODAY()-[Target Resolution Date]))))
Note on K3: Delay Days compares target resolution date with actual resolution date or today.

## Risk Register
Risk Register
Quick Filters: | Project ID |  | Impact |  | Probability |  | Risk Level |  | Owner
Risk ID | Project ID | Risk Description | Impact | Probability | Risk Score | Risk Level | Mitigation Plan | Owner | Status | Remarks
RSK-001 | PRJ-001 | UAT defect leakage may delay release | 4 | 4 |  |  | Daily defect review | Ananya Rao | Open
RSK-002 | PRJ-002 | Vendor API readiness risk | 5 | 5 |  |  | Executive escalation | Rohit Menon | Open
RSK-003 | PRJ-004 | Performance may not meet SLA | 4 | 4 |  |  | Load testing and tuning | Vikram Shah | Open
Note on F3: Risk Score = Impact x Probability.

## Resource Tracker
Resource Tracker
Quick Filters: | Resource Name |  | Role |  | Project ID |  | Module
Resource Name | Role | Project ID | Module | Allocation % | Start Date | End Date | Current Workload | Remarks
Priya Nair | Frontend Engineer | PRJ-001 | Login | 60% | 2026-01-20 | 2026-07-12
Arjun Patel | Backend Engineer | PRJ-001 | Payments | 80% | 2026-03-15 | 2026-07-12
Leena Das | Business Analyst | PRJ-002 | Workflow | 75% | 2026-02-15 | 2026-08-15
Nikhil Verma | Integration Engineer | PRJ-002 | Integration | 90% | 2026-03-01 | 2026-08-15
Imran Ali | ML Engineer | PRJ-004 | KYC | 70% | 2026-04-01 | 2026-08-21

## Change Request Tracker
Change Request Tracker
Quick Filters: | Project ID |  | Requested By |  | Approval Status |  | Status
CR ID | Project ID | Change Description | Requested By | Requested Date | Impact Analysis | Effort Estimate | Approval Status | Target Date | Status | Remarks
CR-001 | PRJ-001 | Add transaction nickname field | Business | 2026-05-10 | Medium UI and API impact | 6 days | Approved | 2026-06-20 | In Progress
CR-002 | PRJ-004 | Add CKYC validation | Compliance | 2026-05-24 | High integration impact | 14 days | Pending | 2026-07-05 | Open

## UAT Testing Tracker
UAT Testing Tracker
Quick Filters: | Project ID |  | Module |  | Tester |  | Result
Test Case ID | Project ID | Module | Test Scenario | Tester | Test Date | Result | Defect ID | Retest Status | Remarks
TC-001 | PRJ-001 | Payments | Verify successful UPI payment | QA Analyst 1 | 2026-06-02 | Fail | ISS-001 | Pending | Timeout observed
TC-002 | PRJ-003 | Reports | Generate monthly compliance report | QA Analyst 2 | 2026-04-18 | Pass |  | Not Required

## Deployment Tracker
Deployment Tracker
Quick Filters: | Project ID |  | Environment |  | Deployed By |  | Deployment Status
Deployment ID | Project ID | Environment | Deployment Date | Version | Deployed By | Deployment Status | Rollback Required | Remarks
DEP-001 | PRJ-003 | Production | 2026-05-06 | v1.0.0 | Release Manager | Completed | No | Successful release
DEP-002 | PRJ-001 | UAT | 2026-06-01 | v0.9.2 | Release Manager | Successful | No | UAT build